Renewable Lesotho RBF Platform

Project Lifecycle Walkthrough

From approved contract to paid milestones — every verification step (Field, DoE, RMT, TAC, PSC, Audit) and how to clear each blocker

Prepared from the platform source code (develop / test branch), October 2026

Audience: QA testers, project team and anyone running an end-to-end lifecycle test

Contents

1. How the lifecycle works

1.1 The payment approval chain

1.2 Roles and where they work

2. Before you start: accounts, settings and test data

2.1 Accounts you need

2.2 Check Platform Configuration first (Super Admin)

2.3 Files and data to prepare

3. Stage A — Contract (PBA)

3.1 RMT generates the PBA

3.2 Vendor uploads the signed agreement

3.3 RMT approves or rejects

4. Stage B1 — Project assignment and milestones

5. Stage B2 — Project setup and RMT setup review

5.1 Vendor completes setup

5.2 RMT reviews the setup

6. Stage C1 — Submitting installations (Vendor)

6.1 Meter data (both IoT and Manual projects)

7. Stage C2 — Field verification and DoE review

7.1 Field Verifier verifies each installation

7.2 DoE Officer reviews verifications

7.3 Vendor fixes a flagged installation

8. Stage C3 — RMT data reviews (meter data and anomaly flags)

8.1 Meter data batches

8.2 Anomaly flags

9. Stage C4 — Oversight by PSC, DoE and Auditor

9.1 Closing an audit case

10. When does a milestone become claimable?

10.2 Milestone 1 at 0% — RMT decides whether the vendor proceeds

10.1 "Milestone is not claimable yet" checklist

11. Stage D1 — Submitting a payment claim (Vendor)

12. Stage D2 — Claim approval chain: RMT → TAC → PSC → payment

12.1 RMT Managerial Review

12.2 TAC Technical Review

12.3 PSC Financial Authorization

12.4 RMT Payment Confirmation (marks the claim paid)

12.5 Payment holds (HTTP 409)

13. Stage D3 — Milestone completion review and the next milestone

13.1 Repeating for M2 and M3

14. Troubleshooting

14.1 Quick fix table

14.2 "Server Error 500" or being sent back to the login page

Appendix A — Status reference

Project status

Milestone status

Installation status

Claim status

Appendix B — End-to-end test checklist

If the contents list is empty, right-click it in Word and choose Update Field.

# 1. How the lifecycle works

A project on this platform moves through four big phases. Within each phase, different roles must act in a fixed order. The project's own status stays Active for the whole delivery phase — progress is tracked through milestone, installation and claim statuses instead.

| Phase | What happens | Who acts |
| --- | --- | --- |
| A. Contract | PBA (contract) generated → vendor uploads signed PDF → RMT approves | RMT, Vendor |
| B. Project start | RMT assigns the project with 3 milestones → vendor completes setup → RMT approves setup (project becomes Active) | RMT, Vendor |
| C. Delivery & verification | Vendor submits installations and meter data → Field Verifier verifies on site → DoE acknowledges / requests re-verification → RMT reviews meter data and anomaly flags → PSC/DoE/Auditor oversight | Vendor, Field Verifier, DoE, RMT, PSC, Auditor |
| D. Milestones & payment | M1 (0% by default): conditions met → RMT records the completion decision (no claim). M2 and M3: milestone becomes claimable → vendor submits claim → RMT approves → TAC endorses → PSC approves → RMT confirms payment → RMT records the completion decision | Vendor, RMT, TAC, PSC |

## 1.1 The payment approval chain

Every milestone with money attached (M2 and M3 by default) goes through the same chain. A 0% milestone (M1 by default) has no claim: it goes straight to step 6 once its conditions are met.

| # | Step | Role | Claim status after |
| --- | --- | --- | --- |
| 1 | Vendor submits claim | Vendor | Submitted |
| 2 | RMT Managerial Review — approve in full or partially (or return) | RMT / Super Admin | RMT Approved |
| 3 | TAC Technical Review — Endorse Claim (or push back) | TAC Member | TAC Endorsed |
| 4 | PSC Financial Authorization — Approve Payment (or reject) | PSC | PSC Approved |
| 5 | RMT Payment Confirmation — enter bank/IFMS reference | RMT / Super Admin | Completed (shown as Paid) |
| 6 | Milestone completion review — Verify & proceed / close / transfer / complete | RMT / Super Admin | Next milestone can unlock |

NOTE  DoE does not approve claims. The DoE Officer's role is monitoring: acknowledging field verifications, requesting re-verification, site visits, monthly KPI reviews and raising flags. A DoE flag can still hold a payment (see Section 12).

There is no separate Finance role. Marking a claim paid is done by RMT (or Super Admin) with Confirm Payment.

## 1.2 Roles and where they work

| Role (as shown in the app) | Main screens for this lifecycle | Responsibilities |
| --- | --- | --- |
| Vendor | Contracting, Projects Hub (tabs: Planning, Field Work, Device Readings, Anomaly Flags, Payments), Payment Claims | Sign contract, complete setup, submit installations & meter CSV, fix flagged items, submit/resubmit claims |
| RBF Management Team (RMT) | Award Management, Projects Hub, Disbursements, Audit & Oversight | Approve contract, assign project, review setup, review meter data & anomalies, first claim approval, confirm payment, milestone completion decision |
| Platform Administrator (Super Admin) | Projects, Payments, User Management, Master Data, Platform Configuration | Everything RMT does except assigning a project; sets inclusion targets and platform settings |
| Field Verifier | Verifications, Map View | Blind on-site verification of each installation in their district |
| DoE Officer | Field Verification, Regional Monitoring, KPI Review, Verification / Monitoring Issues | Acknowledge or request re-verification; site visits; KPI reviews; flags (own region only) |
| TAC Member | Claim Reviews | Technical endorsement of RMT-approved claims |
| Project Steering Committee (PSC) | Disbursements, Project Monitoring, Flagged Issues, PSC Oversight | Final financial approval; oversight reviews and flags (can hold payment) |
| Auditor | Audit Cases, Anomalies, Corrective Actions | Independent audit cases; can hold payment while a case is open |

# 2. Before you start: accounts, settings and test data

## 2.1 Accounts you need

Log in to each role in a separate browser or private window so the sessions do not overwrite each other (the app stores the login token per browser).

- Super Admin — for platform settings and inclusion targets.

- RMT user — contract approval, project assignment, setup review, claim approval, payment confirmation.

- Vendor user — must own a bid on a tender that is already Awarded.

- Field Verifier — their verification zone must match the project district. If no verifier covers the district, no verification task is assigned and installations stay Submitted forever.

- DoE Officer — their region must include the project's district (DoE can only act in its own region).

- TAC Member and PSC user — for the claim approval chain.

- Auditor (optional) — only needed if you test audit holds.

## 2.2 Check Platform Configuration first (Super Admin)

Open the Super Admin portal → Platform Configuration and confirm these values before assigning the project:

- Inclusion targets (female-headed / vulnerable / low-income %). Defaults are 50 / 30 / 60.

- Partial payment minimum — default 70%.

- National / main programme budget — if configured, payment confirmation fails when the remaining balance is lower than the claim.

KNOWN ISSUE  With the default targets, Milestone 3 can never become claimable. Each installation has exactly one household type (Standard, Female Headed, Vulnerable or Low Income), and the KPI counts each type as a share of all verified installations. Milestone 3 requires all three targets at once — 50% + 30% + 60% = 140% of installations, which is impossible.

Workaround for testing: before assigning the project, have the Super Admin set targets that add up to 100% or less (e.g. 40 / 20 / 30). Note that a project target of 0 falls back to the platform default, so you cannot switch a target off by entering 0.

Permanent fix (needs a decision): either let one household carry several inclusion attributes, or treat the three targets as alternatives. Raise this with the product owner.

## 2.3 Files and data to prepare

| Item | Rules enforced |
| --- | --- |
| Signed contract | PDF only, max 10 MB |
| Setup documents: team roster, equipment plan, compliance documents, insurance certificate | PDF or DOCX, max 5 MB each |
| Device brand and model | Must match the awarded bid exactly |
| Installation site photos | Up to 5 per installation, max 5 MB each; plus a proof-of-sale receipt |
| Installation GPS | Inside Lesotho and inside the project's assigned district; keep installations more than 10 m apart |
| Serial numbers and Beneficiary IDs (NID) | Unique across the whole programme — reuse is rejected |
| Verifier GPS | Must be within 50 m of the vendor's GPS or the verification is automatically Flagged |
| Meter data CSV | CSV only, max 5 MB; meter_id or installation_id must match an installation on this project |

TIP  For a quick end-to-end test, use a small installation target (e.g. 5). Milestone 2 needs 80% verified (4 of 5) and Milestone 3 needs 100% (5 of 5) by default.

# 3. Stage A — Contract (PBA)

## 3.1 RMT generates the PBA

- Log in as RMT → Award Management. The tender must already be Awarded.

- Generate the PBA package for the awarded vendor. Contract status becomes Generated and the vendor receives "PBA Package Ready".

## 3.2 Vendor uploads the signed agreement

- Log in as Vendor → Contracting.

- Download the PBA, sign it, and click Submit signed agreement to upload the PDF (max 10 MB).

- Contract status becomes Submitted; RMT receives "Contract Uploaded".

## 3.3 RMT approves or rejects

- As RMT → Award Management → Contract Review.

- Click Approve contract → status Approved; vendor is notified.

- Or click Reject contract and fill "Reason for rejection". The contract returns to Generated and the vendor must upload again (repeat 3.2).

WATCH OUT  "Signed contract must be uploaded as a PDF." / "…must not exceed 10MB." — re-export the scan as PDF and compress it.

# 4. Stage B1 — Project assignment and milestones

Only an RMT user can assign the project (not Super Admin).

- RMT → Award Management → Project Assignment → Assign project (or Assign this lot).

- Fill the Milestone Assignment form:

  - Project duration: 6, 12 or 18 months.

  - Installation target (at least 1) and technology (must be one of the tender's technologies).

  - Energy target (kWh/month, at least 0.01).

  - District(s): at least one. Installations must be inside these districts.

  - Verification method: IoT or Manual (this changes what setup asks for).

  - Disbursement split M1/M2/M3 — default 0 / 50 / 50, must total 100%. M1 may be 0%; M2 and M3 must each be at least 1%.

  - Installation % required for M2/M3 — default 80/100; M3 cannot be lower than M2.

  - Female / vulnerable / low-income targets — read-only unless you are Super Admin (see the Known Issue in 2.2).

- Click Save & Assign Project.

The system creates the project with status Setup Pending and three milestones:

| Milestone | Initial status | Amount | Unlocks when |
| --- | --- | --- | --- |
| M1 — Mobilization | Pending | Contract value × M1 % (0 by default) | Setup approved (project Active) → goes to RMT verification (Section 10.2) |
| M2 — {M2%} Implementation | Locked | Contract value × M2 % | See Section 10 |
| M3 — Final | Locked | Contract value × M3 % (absorbs rounding) | See Section 10 |

WATCH OUT  "Contract status must be approved before assigning milestones." — finish Stage A first.

"This contract already has an assigned project." — the project already exists; find it in Projects Hub.

"Milestone disbursement percentages must total 100%…" — fix the M1/M2/M3 split.

# 5. Stage B2 — Project setup and RMT setup review

## 5.1 Vendor completes setup

- Vendor → Projects Hub → open the project → Complete Project Setup (opens the Planning tab).

- Fill all four sections:

  - Section A — Team & Resources: team roster file, equipment plan file.

  - Section B — Site Preparation: site status, work schedule start and end (end on or after start), compliance documents, insurance certificate.

  - Section C — Technology Details: device brand and model (must match the awarded bid), technology tier 1–5.

  - Section D — Verification Method: IoT → meter API endpoint and token; Manual → tick "I confirm the manual verification method and readiness requirements for this project."

- Tick all 5 pre-deployment checklist items (team, equipment, site, safety, logistics).

- Use Save Draft at any time; when complete click Submit Project Setup. Project status → Setup Under Review.

## 5.2 RMT reviews the setup

- RMT → Projects Hub → open the project → Start Review.

- Choose one:

  - Approve Setup → Approve: project becomes Active and installation submission unlocks. Milestone 1's conditions are now met: with the default 0% it goes to RMT verification (Section 10.2); if RMT gave it a share it becomes claimable.

  - Request Changes → write notes → Send Change Request: status Setup Changes Requested. Vendor edits and clicks Resubmit Project Setup.

  - Reject Setup → notes → Reject: status Setup Rejected. Vendor must contact RMT; they can request a change to reopen it.

WATCH OUT  "This field is required before submitting setup." — a file or field in Sections A–D is missing.

"Device brand must match the awarded bid's device brand…" — copy the brand/model exactly from the bid.

"All pre-deployment checklist items must be completed." — tick all five boxes.

"Project setup can only be submitted after the contract is approved." — Stage A is not finished.

"Notes are required for this action." (RMT) — Request Changes and Reject need notes.

Approved setups are locked: "Change requests are no longer allowed."

# 6. Stage C1 — Submitting installations (Vendor)

- Vendor → project → Field Work tab → + Submit New Installation.

- Fill in: serial number, beneficiary ID (NID), optional phone, household type (Standard / Female Headed / Vulnerable / Low Income), optional household profile (members, men, women, income level, income source), GPS latitude/longitude, optional smart meter ID and kWh reading, up to 5 site photos and the proof-of-sale receipt.

- Click Submit Installation. Status Submitted (yellow on the map). A verification task is created automatically for the Field Verifier who covers that district.

- Repeat until you reach the number of installations needed for the next milestone.

NOTE  Household type is what counts for inclusion KPIs, and the Field Verifier can overwrite it on site. The household profile fields (members, men/women, income level, income source) are stored as evidence only — they do not affect milestones or payments.

Only Verified installations count toward milestone progress and inclusion targets.

## 6.1 Meter data (both IoT and Manual projects)

- Field Work / Device Readings → Upload Meter Data CSV.

- The batch starts as pending review. RMT reviews it (Section 8.1).

- Milestones 2 and 3 need a meter reading from the last 30 days and no batch left in Flagged or Correction Requested.

WATCH OUT  "Complete project setup before submitting installations." — setup is not approved yet.

"Location is outside Lesotho…" / "…fall outside the assigned district" — capture GPS at the actual site inside the project district.

"Serial number … is already registered…" / "Beneficiary … already has installation…" — each device and each household can only be reported once programme-wide.

"…men + … women is more than the … people in the household." — fix the household counts.

"These coordinates are within 10m of an existing installation…" — saved, but a duplicate-GPS anomaly is raised that RMT must resolve.

"This installation has been field-verified; its evidence is locked." — edits are only allowed before verification. Installations cannot be deleted.

# 7. Stage C2 — Field verification and DoE review

## 7.1 Field Verifier verifies each installation

Verification is blind: until the verifier submits, they do not see serial, meter, beneficiary, household or photo data recorded by the vendor.

- Field Verifier → Verifications → open the task.

- Step Location & Device: capture verifier GPS on site; confirm the system is working and the serial number is visible and matches.

- Step Beneficiary Check: beneficiary present? gender seen; household type (this overwrites the vendor's value).

- Step Submit Verification: choose the outcome — Verified, Partial or Flagged (Partial/Flagged need a reason); add at least 1 photo (max 5, 5 MB each); click Submit Verification.

| Outcome | Installation becomes | Effect |
| --- | --- | --- |
| Verified | Verified (green) | Counts toward milestones and KPIs |
| Partial | Stays Submitted | Does not count yet; needs follow-up |
| Flagged | Flagged (red) | Anomaly flag created; vendor can Fix & Resubmit |
| Any outcome, GPS > 50 m from vendor GPS | Forced to Flagged | "Location mismatch: {d}m" |

Once submitted, the verification is locked. To change it, a reviewer must request re-verification.

## 7.2 DoE Officer reviews verifications

- DoE Officer → Field Verification.

- For a Verified or Flagged result, click Accept / Acknowledge (once per round), or

- Click Request Re-verification and give a reason (at least 10 characters). The task becomes Reverification Required, the installation returns to Submitted (yellow), RMT and the verifier are notified, and the verifier sees Re-verify in their list.

NOTE  RMT and Super Admin can also request re-verification. DoE can only act on installations in its own region ("You can only review verifications in your region.").

## 7.3 Vendor fixes a flagged installation

- Vendor → Field Work → the flagged row → Fix & Resubmit.

- Describe the correction (at least 10 characters), update GPS/evidence, click Resubmit for verification.

- The installation returns to Submitted and the verifier gets a re-verification task.

WATCH OUT  Maximum 3 resubmissions per installation. After that the UI shows "No resubmissions left — contact RMT".

Field Verifier errors: "You can only verify installations in your assigned district." (wrong zone); "flag_reason is required…"; "You can upload at most 5 site photos."

"Field verification is paused while the vendor is under suspension." — the vendor is suspended/blacklisted.

# 8. Stage C3 — RMT data reviews (meter data and anomaly flags)

## 8.1 Meter data batches

RMT / Super Admin → project → Device Readings. For each batch:

- Verify — accepts the batch (notes are required if the batch was flagged).

- Reject — reason required.

- Request correction — reason required, optional due date. The vendor uploads a corrected CSV.

- Individual readings can be rejected or restored. Rejected readings never count toward KPIs.

WATCH OUT  A batch left in Flagged or Correction Requested blocks Milestones 2 and 3 from becoming claimable.

## 8.2 Anomaly flags

Anomaly flags are raised automatically (location mismatch, verification distance, duplicate GPS, zero uptime, output deviation, etc.). RMT handles them on the Anomaly Flags tab:

- Start investigation (status Under Investigation). A flag must be under investigation before it can be resolved.

- If the vendor must act: Request correction or Request evidence — needs notes, corrective action and a due date (default 14 days).

- Vendor → Anomaly Flags → respond (at least 10 characters, optional jpg/png/webp/pdf ≤ 5 MB) → Send to RMT. The flag returns to Under Investigation.

- RMT closes it as Resolved or False positive — needs investigation notes, corrective action, decision reason and an evidence reference.

WATCH OUT  Overdue vendor-action flags are escalated automatically by a daily job; escalated flags hold payment.

Milestone 2 is blocked by any open zero_uptime or output_deviation flag. Milestone 3 requires zero unresolved flags of any kind.

# 9. Stage C4 — Oversight by PSC, DoE and Auditor

These checks run alongside delivery. They don't move the project forward, but any of them can hold a payment until resolved.

| Who | Action | Can it hold payment? |
| --- | --- | --- |
| PSC | Oversight review: Compliant / Delayed / Flagged / Comment; "Flag Project" | Yes — if "Hold milestone payments" is ticked, or the flag is on a claim/disbursement, until the follow-up is resolved |
| DoE Officer | Oversight flag or comment; site monitoring visit (photos, max 10); monthly KPI review (On track / Needs attention / At risk) | Yes — a flag with hold ticked, or a site visit that recorded "system not working" with an open follow-up |
| RMT / Super Admin | Oversight flag or comment; resolve follow-ups (note required: "Describe how the issue was resolved.") | Yes, same rules |
| Auditor | Audit case: Draft → Under Review → Evidence Collected → Finding Recorded → Management Response → Audit Finalized → Closed | Yes — an in-progress case on a claim, or a major/critical finding with an open corrective action |

## 9.1 Closing an audit case

- Auditor collects evidence (required before "Evidence Collected") and records a finding (at least 20 characters). Exceptions and non-compliance need a corrective action.

- RMT gives a management response (at least 10 characters) and moves the corrective action Open → In Progress → Implemented.

- Auditor marks the corrective action Verified, finalizes and closes the case. Only then is the payment hold lifted.

# 10. When does a milestone become claimable?

The system re-checks eligibility automatically whenever KPIs refresh. When a milestone unlocks, the vendor gets "Milestone {n} Claimable" and it appears under Claimable Milestones on the Payments tab.

| Condition | M1 | M2 | M3 |
| --- | --- | --- | --- |
| Project open, contract approved | ✔ | ✔ | ✔ |
| Project setup approved | ✔ |  |  |
| Result when conditions are met | 0%: RMT verification >0%: claimable | Claimable | Claimable |
| Previous milestone's completion review = Proceed or Transfer |  | ✔ (M1) | ✔ (M2) |
| Previous milestone paid |  |  | ✔ |
| Verified installations ÷ target |  | ≥ M2 % (default 80%) | ≥ M3 % (default 100%) |
| Female-headed share ≥ target |  | ✔ | ✔ |
| Vulnerable and low-income shares ≥ target |  |  | ✔ |
| Anomaly flags |  | No open zero_uptime / output_deviation | Zero unresolved flags |
| Meter reading in the last 30 days |  | ✔ | ✔ |
| No meter batch Flagged / Correction Requested |  | ✔ | ✔ |

## 10.2 Milestone 1 at 0% — RMT decides whether the vendor proceeds

With the default split, Milestone 1 (Mobilization) carries 0%, so there is nothing to claim. It is not skipped: once its conditions are met (contract approved and project setup approved), it goes straight to RMT verification.

- When setup is approved, M1 shows AWAITING VERIFICATION. RMT, Super Admin and the vendor receive "Milestone 1 Awaiting Verification".

- RMT / Super Admin → project → Milestones → the Milestone Completion Review panel on M1.

- Choose Verify & proceed to next milestone, Verify & close project or Verify & transfer to another vendor, add verification notes and submit.

- On proceed (or transfer), M1 shows VERIFIED and Milestone 2 can unlock once its own conditions are met. On close, the project is closed and M2/M3 are cancelled.

NOTE  The vendor sees: "This milestone is set to 0% disbursement, so there is no payment claim. Once its conditions are met, the RBF Management Team verifies it and decides whether you proceed to the next milestone." The same flow applies to any milestone whose share is 0%.

## 10.1 "Milestone is not claimable yet" checklist

- Has RMT recorded the completion decision on the previous milestone (Section 13; for a 0% M1, Section 10.2)? For a paid milestone it must also be paid. This is the most common blocker.

- Open the project's KPI tab: compare verified count vs target and each inclusion % vs target.

- Are any installations still Submitted (no verifier assigned in that district?) or Flagged (needs Fix & Resubmit)?

- Open Anomaly Flags: resolve or mark false positive anything open.

- Open Device Readings: is there a reading in the last 30 days, and no batch Flagged / Correction Requested?

- For M3: do the three inclusion targets add up to 100% or less? (See Known Issue in 2.2.)

# 11. Stage D1 — Submitting a payment claim (Vendor)

- Vendor → Projects Hub → project → Payments tab → Claimable Milestones.

- Open Claim Composer for the milestone. Enter completion date, actual beneficiaries, actual female beneficiaries, implementation notes and evidence files.

- Click Submit Payment Claim. The claim is Submitted, the milestone becomes claimed, and RMT is notified.

NOTE  The claim amount is fixed by the system: milestone amount + any shortfall carried over from an earlier partial payment. Whatever is typed in the amount field is replaced.

WATCH OUT  "A claim for this milestone already exists…" — one claim per milestone; track the existing one.

"This milestone claim was returned for completion. Fix the listed items and resubmit the existing claim." — use Resubmit Claim, not a new claim.

"Milestone {n} is not claimable yet…" — work through checklist 10.1.

"Milestone {p} must be completed and verified by the RBF Management Team…" — RMT must record the completion decision on the previous milestone.

"Your vendor account is suspended or blacklisted. Payment claims are on hold for audit."

# 12. Stage D2 — Claim approval chain: RMT → TAC → PSC → payment

The approval queue appears as Disbursements / Payments (RMT, Super Admin, PSC) and Claim Reviews (TAC). Each row has the action for the current stage.

## 12.1 RMT Managerial Review

- RMT → Disbursements → row action RMT Review.

- Check verified delivery, evidence and any listed blockers. Choose:

  - Approve in full → Approve → status RMT Approved.

  - Approve partially → enter assessed % and list the deficiencies → Approve Partial Payment. Allowed only if at least 70% (configurable) is delivered and verified, and never on the final milestone. The unpaid part is carried into the next milestone's claim.

  - Return for completion → list what the vendor must complete → Return to Vendor → status Returned. The vendor fixes items and clicks Resubmit Claim (status back to Submitted).

## 12.2 TAC Technical Review

- TAC → Claim Reviews → TAC Review.

- Endorse Claim → status TAC Endorsed, or

- Push Back to RMT → status back to Submitted; RMT must review again.

## 12.3 PSC Financial Authorization

- PSC → Disbursements → PSC Review.

- Optionally View Bank Details — the full account number is revealed only on request and the action is logged.

- Approve Payment → status PSC Approved, or Reject Claim → status Rejected (the milestone becomes claimable again and the vendor files a new claim).

## 12.4 RMT Payment Confirmation (marks the claim paid)

- After the bank transfer is made, RMT → Disbursements → Confirm Payment.

- Review the Disbursement Sheet (vendor bank details), paste the bank receipt or IFMS transaction ID into Transaction/Reference ID, click Submit.

- Claim status → Completed (shown as Paid or Paid (partial)); milestone → paid; a disbursement record is created; carry-overs are settled; a milestone completion review opens.

## 12.5 Payment holds (HTTP 409)

At any approval step you may see: "Payment is on hold until these findings are closed: …" and the approve button is disabled. Clear each listed item:

| Hold source | How to clear it |
| --- | --- |
| High / critical, zero_uptime, output_deviation or escalated anomaly flag | RMT investigates and resolves or marks false positive (Section 8.2) |
| Oversight review with "Hold milestone payments" (PSC / DoE / RMT) | Resolve the follow-up with a resolution note |
| DoE site visit recorded "system not working" | Fix the system, then resolve the visit's follow-up |
| Audit case in progress / major finding with open corrective action | Complete the audit workflow until the case is Closed (Section 9.1). Vendors do not see audit blockers. |
| Vendor suspended or blacklisted | Claims stay Held/Audit; resolve through Blacklisting (Super Admin) |

WATCH OUT  "Only submitted claims can be approved by RMT." / "Claim must first be approved by RMT before TAC endorsement." / "…endorsed by TAC before PSC approval." / "…PSC approved before it can be marked as paid." — the claim is at a different stage; refresh and check its status.

"payment_reference is required." — enter the transaction ID.

"Insufficient National/Main Program Budget. Remaining balance is …" — the Super Admin must raise the budget in Platform Configuration.

"Partial payment needs at least {min}%…" / "The final milestone cannot be paid partially…" — use Return for completion instead.

"The disbursement sheet is available only after PSC approval."

# 13. Stage D3 — Milestone completion review and the next milestone

After every paid milestone — and for a 0% milestone, as soon as its conditions are met — RMT or Super Admin must record a decision in the Milestone Completion Review panel (status "Awaiting RBF / Super Admin verification"). The next milestone stays locked until this is done.

| Decision | Button | Result |
| --- | --- | --- |
| Proceed | Verify & proceed to next milestone | Next milestone can unlock once its conditions are met |
| Transfer | Verify & transfer to another vendor | Project moves to a new (not suspended/blacklisted) vendor; next milestone can unlock |
| Close | Verify & close project | Project Closed; later unpaid milestones Cancelled; pending carry-overs forfeited |
| Complete (final milestone only) | Verify & complete project | Project Completed and archived |

NOTE  Paying the final milestone does not close the project by itself, even though the Confirm Payment screen mentions it. RMT must still choose Verify & complete project.

## 13.1 Repeating for M2 and M3

- Keep submitting installations until verified count reaches the M2 % (default 80% of target).

- Keep inclusion shares, meter data and anomaly flags in order (Section 10).

- Submit the M2 claim → RMT → TAC → PSC → Confirm Payment → Verify & proceed.

- Reach 100% verified, all three inclusion targets, zero open flags → submit the M3 claim → full chain → Verify & complete project.

# 14. Troubleshooting

## 14.1 Quick fix table

| Symptom | Likely cause | Fix |
| --- | --- | --- |
| Installation stays Submitted, verifier sees nothing | No Field Verifier has a verification zone for that district | Super Admin → User Management: set the verifier's zone to the project district |
| DoE can't see/act on a verification | Installation is outside the DoE officer's region | Use a DoE officer for that region |
| Verification auto-Flagged "Location mismatch" | Verifier GPS > 50 m from vendor GPS | Vendor corrects GPS via Fix & Resubmit, or verifier re-captures on site |
| "No resubmissions left — contact RMT" | 3 resubmissions used | RMT reviews the installation directly / requests re-verification |
| M2 never unlocks | M1 completion decision missing, female share below target, stale meter data, or open zero_uptime/output_deviation flag | Work through checklist 10.1 |
| M3 never unlocks | Inclusion targets add up to more than 100%, or any open anomaly flag | See Known Issue 2.2; resolve all flags |
| Approve button disabled | Payment hold | Clear the listed holds (12.5) |
| "Bank details are available to PSC only after…" | Claim not yet TAC Endorsed | Wait for TAC endorsement |
| Project shows Halted | Vendor blacklisted or linked to blacklisted serials/beneficiaries | Super Admin reviews blacklisting; claims and disbursements are on Held/Audit |

## 14.2 "Server Error 500" or being sent back to the login page

Testers on the deployed site have reported that a create/update action sometimes fails with a 500 error and then works after reloading the page, and that they are sometimes logged out. These are platform issues, not mistakes in the workflow. Likely causes found in the code:

| # | Cause | What you see | Fix (development team) |
| --- | --- | --- | --- |
| 1 | When the login token expires (30 min), the backend answers 403 instead of 401, so the app never refreshes the token | Errors after ~30 minutes; reload sends you to the login page | Put JWTAuthentication first (or remove Session/Basic auth) in DRF settings; also refresh on 403 token_not_valid in src/api.ts |
| 2 | Any server error during token refresh logs the user out; several refreshes can run at once | Random logouts during busy periods or deployments | Only log out on 400/401 from the refresh endpoint; share one in-flight refresh |
| 3 | Stale database connections (CONN_MAX_AGE without health checks) | First action fails with 500, retry works | Set CONN_HEALTH_CHECKS = True |
| 4 | Redis read on every request with no error handling | Every action fails with 500 for a short time | Wrap the cache read in try/except or add Redis timeouts and retries |
| 5 | Only 3 gunicorn workers; PDF rendering, email and Prospect calls block them | Slow pages, 502/504 shown as server error | More workers/threads, timeouts on PDF rendering, send email in the background |
| 6 | Every push to develop redeploys the live server | Failures and logouts around deploy time | Deploy develop to a separate environment, or deploy outside test hours |

TIP  While these fixes are pending: if you get a 500, reload and retry once before reporting a bug.

If you are logged out, log in again. Changes saved before the error are kept. Check the item's status before resubmitting so you don't create a duplicate.

Avoid running tests while a deployment is in progress.

# Appendix A — Status reference

## Project status

| Status | Meaning |
| --- | --- |
| Setup Pending | Assigned; vendor has not submitted setup |
| Setup Under Review | Submitted, waiting for or under RMT review |
| Setup Changes Requested | Vendor must update and resubmit setup |
| Setup Rejected | Setup rejected; contact RMT |
| Active | Delivery phase — installations, verification and claims |
| Halted | Vendor blacklisted; payments held |
| Completed | Final milestone paid and completed by RMT |
| Closed | Closed early by RMT completion decision |

## Milestone status

| Status | Meaning |
| --- | --- |
| Locked | Conditions not met yet |
| Pending / Claimable | Vendor may submit a claim |
| Awaiting Verification (0% milestone) | Conditions met; RMT must record the completion decision |
| Verified (0% milestone) | RMT has recorded the decision |
| Claimed | Claim in the approval chain |
| Paid | Payment confirmed; completion review required |
| Cancelled | Project closed before this milestone |

## Installation status

| Status | Meaning |
| --- | --- |
| Submitted (yellow) | Awaiting field verification or re-verification |
| Verified (green) | Counts toward milestones and KPIs |
| Flagged (red) | Problem found; vendor must Fix & Resubmit (max 3) |
| Paused / Terminated | Vendor suspended / terminated |

## Claim status

| Status | Next action by |
| --- | --- |
| Submitted | RMT — RMT Review |
| Returned (Returned for completion) | Vendor — Resubmit Claim |
| RMT Approved | TAC — Endorse or Push Back |
| TAC Endorsed | PSC — Approve Payment or Reject |
| PSC Approved | RMT — Confirm Payment |
| Completed (Paid / Paid (partial)) | RMT — Milestone completion review |
| Rejected | Vendor — submit a new claim |
| Held/Audit | Super Admin / Auditor — resolve blacklisting or audit |

# Appendix B — End-to-end test checklist

| ☐ | Role | Step |
| --- | --- | --- |
| ☐ | Super Admin | Inclusion targets sum ≤ 100%; budget configured; verifier zone and DoE region set |
| ☐ | RMT | PBA generated |
| ☐ | Vendor | Signed contract uploaded |
| ☐ | RMT | Contract approved; project assigned (Save & Assign Project) |
| ☐ | Vendor | Setup submitted |
| ☐ | RMT | Setup approved → project Active |
| ☐ | RMT | M1 (0%) shows AWAITING VERIFICATION; completion review: Verify & proceed |
| ☐ | Vendor | Installations submitted (≥ M2 %), meter CSV uploaded |
| ☐ | Field Verifier | All installations verified (one flagged → Fix & Resubmit tested) |
| ☐ | DoE | Verifications acknowledged; one re-verification requested and completed |
| ☐ | RMT | Meter batch verified; anomaly flags resolved |
| ☐ | PSC / DoE / Auditor | Optional: raise a hold, confirm approval is blocked, resolve it |
| ☐ | Vendor → chain | M2 claim through RMT (try partial) → TAC → PSC → Confirm Payment |
| ☐ | RMT | M2 completion review: Verify & proceed |
| ☐ | Vendor → chain | 100% verified, all targets met; M3 claim through the full chain |
| ☐ | RMT | M3 completion review: Verify & complete project → project Completed |